## Local
Done | Task
1. Local test using copy of prod
x | a. Take dev version of Code from TFS and compile.
x | b. Prevent checkin by anyone to dev during this process to prevent bringing in untested code
x | c. Get and log the latest changset id for the dev release. 3486
x | d. Copy latest backups for SchoolObjectModel, StarBridge, CCSD_ODL
x | e. Restore to local databases
x | f. Update config files to point to local database connections copied
x | g. Point other database connections to Prod.
x | h. Bring up the visual studio PortalIntergration-Starbridge/SchoolObjectModelDatabase project
x | i. Run the Publish feature and generate the scripts.
x | j. Review the generated script file and verify expected content is there.
x | i. Steps may contain table alters that require them to be empty.
x | ii. Add code to move data into temp tables, then truncate table, then alter table and then reload appropriate data for the altered table.
x | k. Apply generated scripts to the local SchoolObjectModel database server (restored from backup of prod).
x | l. Ensure scripts ran error free
x | m. Check any tables where data was moved and reloaded, to ensure all data is appropriately loaded.
x | n. Get the latest value for the last item imported and logged in the Starbridge EntityValueChange table
x | · SELECT top 1 [TimeStamp] FROM [Starbridge].[dbo].[EntityValueChange] ORDER BY [TimeStamp] DESC
x | · '2016-08-30 12:34:18.9569055 -06:00'
x | o. Save Script file and check-in. Will be applied again to staging and prod.
x | p. Run Enchilada.cmd and save cmd output
x | q. Review output and verify logged changes
x | r. Re-Run Enchilada.cmd and compare cmd results with previous run (no additional changes should come up.)
x | s. From Sql Management Studio open the starbridge view and confirm the changes logged
SELECT [DestinationSystem]
,[EntityType]
,[DestinationSystemEntityId]
,[SourceSystem]
,[SourceSystemEntityId]
,[TimeStamp]
,[TransactionType]
,[ValueName]
,[PreviousValue]
,[NewValue]
FROM [Starbridge].[dbo].[EntityValueChange]
WHERE [TimeStamp] > '2016-08-30 12:34:18.9569055 -06:00'
ORDER BY [TimeStamp] DESC
x | t. Done local test.

## Staging
Done | Task
Note on Staging test using copy of prod (speed of execution is important as Prod connections can bring in new data from HRAD and Powerschool)
x |  | Compile an x64 Release version for the Prod ensuring release candidate is at specified change sets and no subsequent or unwanted changeset are included.
x |  | Copy existing staging app files to backup
x |  | Copy existing Prod app files to Staging - retaining config files unless there is a new version of this file as well, if so ensure staging version points to staging databases where applicable
|  |  | C:\IT_Portal\StarBridge\CSSD |  | C:\IT_Portal\StarBridge-Staging\CSSD
x |  | Copy the prod json files to staging, check if PortalIntegration.json files are being updated
|  |  | C:\JsonFiles to C:\JsonFiles-Staging |  | C:\IT_Portal\StarBridge\Configuration\PortalIntegration.json to C:\IT_Portal\StarBridge-Staging\Configuration\PortalIntegration.json
x |  | Get copy of Prod db restored to Staging for SchoolObjectModel, StarBridge & CCSD_ODL
Restore Prod Backup of SchoolObjectModel to SchoolObject-Staging, StarBridge to StarBridge-Staging and CCSD_ODL to CCSD_ODL-Staging
x |  | Run the app in staging - taking note of changes, can run multiple times to fully sync the integrations. Take any notes of timing , exceptions, etc.
Setup cmd prompt to run PortalIntegration-starbridge from the staging folder
x | b. Copy files over to 10.154.2.6 (app server) to the staging folder
|  |  | i. | C:\IT_Portal\StarBridge-Staging\CSSD | check that the files were copied from \\IT_Portal\Prod\Source\PortalIntegration-StarBridge\Cssd.IT.PortalIntegration\bin\x64\Release into \\IT_Portal\Prod\Source\PortalIntegration-StarBridge\CSSD
x | c. Copy over the appropriate JSON files from SourceControl to the Prod Application server Json Staging folder
if changes were made to PortalIntegration.json, copy the new version to C:\IT_Portal\StarBridge-Staging\Configuration
x | d. Verify and update database connection to use staging database where prod copies will been restored. Point to prod databases otherwise.
-- | f. Take a Backup of Prod SchoolObjectModel, StarBridge, CCSD_ODL Databases
x | h. On the 10.154.2.5 server, update the database script file to use the staging databases.
x | i. Run the database script against SchoolObjectModel-staging database
x | j. Ensure scripts ran error free
x | k. Check any tables where data was moved and reloaded, to ensure all data is appropriately loaded.
x | l. Get the latest value for the last item imported and logged in the Starbridge EntityValueChange table
| · SELECT top 1 [TimeStamp] FROM [StarBridge-Staging].[dbo].[EntityValueChange] ORDER BY [TimeStamp] DESC |  |  |  |  | 2019-04-01 15:16:17.4469951 -06:00 | 1st run
· Example result: '2016-08-30 12:34:18.9569055 -06:00'
x | m. From the cmd prompt: Run Enchilada.cmd and save cmd output
x | n. Re-Run Enchilada.cmd and save cmd output |  |  |  |  | 2018-11-06 16:00:00.4321260 -07:00 | 2nd run
o. Need for speed now ends.
p. Compare cmd results with previous run (no additional changes should come up.)
x | q. Review output and verify logged changes
r. From Sql Management Studio open the starbridge view and confirm the changes logged
x | SELECT [DestinationSystem]
,[EntityType]
,[DestinationSystemEntityId]
,[SourceSystem]
,[SourceSystemEntityId]
,[TimeStamp]
,[Outcome]
,[ValueName]
,[PreviousValue]
,[NewValue]
FROM [Starbridge-Staging].[dbo].[EntityValueChange]
WHERE [TimeStamp] > '2016-08-30 12:34:18.9569055 -06:00'
ORDER BY [TimeStamp] DESC
x | s. If ok with changes logged then Done staging test.

## Prod
Done | Task
1. Prod implementation (speed of execution is important as Prod connections can bring in new data from HRAD and Powerschool)
x | a. Open remote sessions to App and DB servers.
x | b. On Db server open Sql Management Studio,
x | i. Open a New Query window and paste in a copy of the database Script file
x | ii. ensure the database script file uses the prod SchoolObjectModel database
x | c. On app server copy existing application files to the backup/restore folder.
d. Update config file on staging folder to set database connection to use all prod databases. (ready to copy to prod)
e.
x | f. Turn off the Task Scheduler for PortalIntergation.
g. Take a Backup of Prod SchoolObjectModel, StarBridge, CCSD_ODL Databases
x | h. Setup the cmd prompt to run PortalIntegration-Starbridge from the prod folder
i. Run Enchilada.cmd and save cmd output
j. Speed required from here…
k. Get the latest value for the last item imported and logged in the Starbridge EntityValueChange table
· SELECT top 1 [TimeStamp] FROM [Starbidge].[dbo].[EntityValueChange] ORDER BY [TimeStamp] DESC
· Example result: '2019-04-01 14:06:27.8257471 -06:00'
x | l. Copy application files over from the staging folder to the prod folder
x | l.2 Copy JsonFiles-Staging to JsonFiles folder
x | m. On the 10.154.2.5 server: Run the database script against SchoolObjectModel database
x | n. Ensure scripts ran error free
x | o. Check any tables where data was moved and reloaded, to ensure all data is appropriately loaded.
x | p. From the cmd prompt: Run Enchilada.cmd and save cmd output
q. Re-Run Enchilada.cmd and save cmd output
r. Need for speed now ends.
x | s. Compare cmd results with previous run (no additional changes should come up.)
x | t. Review output and verify logged changes
x | u. From Sql Management Studio open the starbridge view and confirm the changes logged
SELECT [DestinationSystem]
,[EntityType]
,[DestinationSystemEntityId]
,[SourceSystem]
,[SourceSystemEntityId]
,[TimeStamp]
,[TransactionType]
,[ValueName]
,[PreviousValue]
,[NewValue]
FROM [Starbridge].[dbo].[EntityValueChange]
WHERE [TimeStamp] > '2016-08-30 12:34:18.9569055 -06:00'
ORDER BY [TimeStamp] DESC
v. If ok with changes logged then move onto Smoke test.
w. Smoke test the prod application
x. If all is NOT good
i. Restore back application files and databases
ii. Smoke test the old application
iii. If still not good
1. Deal with it.
y. Turn on the Task Scheduler for PortalIntegration.
z. Merge Prod TFS from DEV cutting off at the changeset identifed
aa. Check-in prod merge

## ReportingIntegration
get latest prod release from tfs
do x64 build
get prod db backup and restore to local for SchoolObjectModel_Reporting
Gen db script and run on local
copy prod db to staging db and run same script on staging
Run db script against prod db
Backup the old prod executabes from C:\IT_Portal\ReportingIntegration\CSSD
Copy compiled files to C:\IT_Portal\ReportingIntegration\CSSD
Disable task scheduler
Run admin cmd prompt against C:\IT_Portal\ReportingIntegration\bin>ExportToReporting

## EntityIdentifierCache
Stop service
Apply the db upgrade scripts to prod db.
Compiled a debug x64 version of code.
Copy compiled files from local build C:\IT_Portal\Prod\Source\SharePointOnlineIntegration\EntityIdentifierCacheService\bin\x64\Debug to \\spapp01\IT_Portal\SharePointOnlineIntegration\EntityIdentifierCacheService
Start service

## SPO-Mock
Apply updated C:\IT_Portal\Dev\Source\PortalIntegration\SqlScripts\SharePointOnline Mock\ CreateMockSharePointDatabase.sql
Stop EntiryIdentiferCache Service
Apply SOM database scripts (rename :setvar DatabaseName "SchoolObjectModel" from SchoolObjectModel-staging
Apply EntityIdentiferCache database scripts (rename :setvar DatabaseName "EntityIdentifierCache" from EntityIdentiferCache-Staging
Copy SharePointOnlineIntegration.json with updated migrators from staging to prod C:\IT_Portal\SharePointOnlineIntegration-Staging\Configuration to C:\IT_Portal\SharePointOnlineIntegration\Configuration
Copy CSSD latest complied files from staging to prod C:\IT_Portal\SharePointOnlineIntegration-Staging\CSSD to C:\IT_Portal\SharePointOnlineIntegration\CSSD
Copy EntiryIdentiferCache latest complied files from staging to prod C:\IT_Portal\SharePointOnlineIntegration-Staging\EntityIdentifierCacheService to C:\IT_Portal\SharePointOnlineIntegration\EntityIdentifierCacheService
Start EntiryIdentiferCache Service, and wait a bit to ensure its running ok, ie refresh list of services